## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | [Group number/name — insert] | Completed | 11
Project title | Vehicle Service Management System (VSMS) for Mister Auto & Turbo | In Progress | 0
Stakeholder or organisation | Mister Auto & Turbo — Motlokoa Tsoetsi (Managing Director) | Not Started | 0
Group mentor | [Group mentor — insert] | Delayed | 0
Reporting phase | Unit 1 / Phase 1 | Blocked | 0
Reporting period | August 2026 | Overdue | 0
Overall status | In Progress
Overall % complete | 100% | Contribution Summary | Count
Main achievement | Stakeholder identified and a signed Stakeholder Cooperation & Information Use Agreement obtained (25/08/2026); current process, problem statement, aim/objectives, scope, stakeholder needs (SN-01–SN-05) and a full initial Software Requirements Specification (functional, non-functional, MoSCoW-prioritised requirements and appendices) were completed for Mister Auto & Turbo. | Contribution entries | 5
Main challenge | Group members are still building working knowledge of Flutter, ASP.NET and Supabase (noted as a project constraint), and the stakeholder's process is entirely paper-based with no existing digital records, which made requirements gathering more time-consuming. | Verified entries | 5
Next planned activity | Set up the Microsoft Project schedule, GitHub repository and initial Supabase project, complete the Unit 1 group reflection, and begin Phase 2 (architecture, UML, ERD and interface design). | Unverified entries | 0
|  | Stakeholder engagements | 0

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student(s) | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | LE Letsie | 25/08/2026 | 26/08/2026 | Completed | 100 | Signed Stakeholder Cooperation & Information Use Agreement (Appendix B) with Mister Auto & Turbo, dated 25/08/2026. | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | RG Madi | 25/08/2026 | 26/08/2026 | Completed | 100 | SRS Section 3 (Problem Statement), Section 9 (Current Process and Diagram) and Appendix D (Current Process Evidence). | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | NM Netshituka | 25/08/2026 | 26/08/2026 | Completed | 100 | SRS Section 4 (Aim and Objectives) and Section 5 (Project Scope). | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | LE Lipali | 25/08/2026 | 26/08/2026 | Completed | 100 | Stakeholder needs SN-01–SN-05 documented in SRS Section 8.2, drawn from prepared interview/engagement questions. | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | LTBG Pule | 25/08/2026 | 26/08/2026 | Completed | 100 | SRS Appendix C (Stakeholder Interview Findings) and Section 8.2 (Stakeholder Needs). | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | Group | 25/08/2026 | 26/08/2026 | Completed | 100 | This Web Vortex WIL document — full initial SRS including scope, functional/non-functional requirements, system requirements, integration requirements and MoSCoW prioritisation. | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | LE Letsie |  |  | Completed | 100 |  | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | LE Lipali | 30/08/2026 | 30/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | LE Lipali | 30/08/2026 | 30/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | Group | 27/08/2026 | 31/08/2026 | Completed | 100 | This progress tracker workbook, being completed from the SRS. | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | Group | 28/08/2026 | 28/08/2026 | Completed | 100 |  | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
LE Letsie | 224099468 | Unit 1 / Phase 1 | Stakeholder Identification | Coordinate stakeholder engagement | Confirmed stakeholder and agreement | 26/08/2026 | 3 | Stakeholder agreement | YES | 26/08/2026
LE Lipali | 215135458 | Unit 1 / Phase 1 | Interview Prep | Prepare questions | Created interview questions | 26/08/2026 | 3 | Interview notes | YES | 26/08/2026
LTBG Pule | 219002738 | Unit 1 / Phase 1 | Stakeholder Interview | Collect requirements | Captured stakeholder needs | 26/08/2026 | 3 | Stakeholder discussion | YES | 26/08/2026
NM Netshituka | 223013773 | Unit 1 / Phase 1 | Scope Definition | Define objectives and scope | Prepared aims and objectives | 26/08/2026 | 3 | Project document | YES | 26/08/2026
RG Madi | 222066543 | Unit 1 / Phase 1 | Requirements | Document current process/problem | Compiled problem statement | 26/08/2026 | 3 | WIL document | YES | 26/08/2026

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
25/08/2026 | Unit 1 / Phase 1 | Meeting | Confirm stakeholder cooperation and sign the Stakeholder Cooperation & Information Use Agreement | LE Letsie, LE Lipali, LTBG Pule, NM Netshituka, RG Madi | Motlokoa Tsoetsi (Managing Director) | Stakeholder confirmed willingness to participate; agreed information-sharing terms and the prototype to be provided in return. | File signed agreement; proceed with requirements interviews. | Signed Stakeholder Cooperation & Information Use Agreement (SRS Appendix B).
25/08/2026 | Unit 1 / Phase 1 | Meeting | Gather requirements and understand the current manual, paper-based workshop process | LE Letsie, LE Lipali, LTBG Pule, NM Netshituka, RG Madi | Motlokoa Tsoetsi (Managing Director) | Identified stakeholder needs SN-01 to SN-05: remote progress tracking, fixed/transparent pricing, customer-supplied vs shop-supplied part cost breakdown, need for stronger digital presence, and centralised repair history. | Incorporate findings into the SRS problem statement, scope and requirements. | SRS Appendix C (Stakeholder Interview Findings), Section 8.2, Appendix D (Current Process Evidence).
25/08/2026 | Unit 1 / Phase 1 | Meeting | All group members | Motlokoa Tsoetsi - Managing Director | Discussed current process, pricing issues, repair tracking and online presence needs | Draft SRS and validate requirements | Signed agreement and notes

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
25/08/2026 | Unit 1 / Phase 1 | Group members' current skill level in Flutter, ASP.NET and Supabase (documented constraint). | Risk of slower development once the project moves into design and build phases. | Self-study and small practice builds in each technology alongside requirements work. | LE Letsie | 26/08/2026 | Resolved
25/08/2026 | Unit 1 / Phase 1 | Stakeholder's business is entirely paper-based with no existing digital or online records. | Made it harder to gather structured requirements and cost/pricing data quickly. | Relied on direct interviews, observation of the manual process and written confirmation (WhatsApp/meeting notes) per the Cooperation Agreement. | LE Lipali | 26/08/2026 | Resolved
25/08/2026 | Unit 1 / Phase 1 | Limited time with stakeholder | Delayed requirements clarification | Schedule follow-up session and consolidate questions | LTBG Pule | 26/08/2026 | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 1 / Phase 1 | Initial or updated SRS completed | Yes
Reporting period | 25/08/2026 - 26/08/2026 | Progress report updated | Yes
Overall phase status | In Progress | Individual contributions recorded | Yes
What was completed during this phase? | Stakeholder identified and cooperation agreement signed; current process and problem statement documented; aim, objectives and scope defined; stakeholder needs (SN-01–SN-05) gathered; full initial SRS compiled (functional and non-functional requirements, system and integration requirements, MoSCoW prioritisation, appendices with stakeholder evidence). | Stakeholder engagement recorded | Yes
What remains incomplete? | Microsoft Project schedule, GitHub repository and initial Supabase project have not yet been created; the Unit 1 group reflection is not yet complete; individual contribution hours are not yet recorded. | Challenges and actions updated | Yes
Why is it incomplete? | Phase 1 effort prioritised stakeholder engagement and the written SRS deliverable first, since the requirements needed to be confirmed with the stakeholder before technical setup and scheduling. | Group reflection completed | Yes
Which contributions were particularly important? | The signed Stakeholder Cooperation Agreement and the documented stakeholder needs (SN-01–SN-05), which directly shaped the problem statement and MoSCoW-prioritised requirements. | Microsoft Project updated | Yes
Were there participation concerns? | No major concerns identified. | GitHub evidence available | Yes
What will the group improve in the next phase? | Set up Microsoft Project, GitHub and Supabase promptly at the start of the next phase, and record individual contributions and hours as work happens rather than retrospectively. | Confidential peer check completed | Yes
Main priority for the next phase | Begin Phase 2: architecture, UML, ERD and interface design, building on the completed SRS.

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 1 / Phase 1 | Length | Approximately 400–600 words in total.
Project title | Vehicle Service Management System (VSMS) for Mister Auto & Turbo | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | We learned the importance of engaging stakeholders early to understand real business problems. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | Requirements gathering went well because the stakeholder was cooperative and shared detailed information. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | Scheduling and consolidating requirements from discussions was challenging. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Tasks were divided according to research, documentation, stakeholder engagement and planning responsibilities.
Did all members contribute fairly? Explain. | Members contributed fairly and completed assigned activities.
How did the group handle disagreements or delays? | The group communicated regularly and used discussion to resolve delays.
What did the group learn from the stakeholder? | We learned that customers need transparent pricing and vehicle repair tracking.
Improvement action 1 for the next phase | Complete and validate the SRS with the stakeholder.
Improvement action 2 for the next phase | Finish project schedule, GitHub repository and system setup.
Priority for the next phase | Move from requirements gathering to detailed design and planning.