## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | [Group number/name — insert] | Completed | 21
Project title | Vehicle Service Management System (VSMS) for Mister Auto & Turbo | In Progress | 0
Stakeholder or organisation | Mister Auto & Turbo — Motlokoa Tsoetsi (Managing Director) | Not Started | 0
Group mentor | [Group mentor — insert] | Delayed | 0
Reporting phase | Phase 2 | Blocked | 0
Reporting period | September 2026 | Overdue | 0
Overall status | In Progress
Overall % complete | 100% | Contribution Summary | Count
Main achievement | System Architecture Diagram, Use Case Diagram, Sequence Diagrams (Flutter↔Supabase, ASP.NET↔Supabase), ERD and Figma interface designs (Flutter mobile and ASP.NET web) completed; a Design Alignment Table linking requirements, use cases, ERD entities and interfaces was compiled; and the Phase 2 System Design was reviewed and signed off by the stakeholder, Motlokoa Tsotesi (25/09/2026). | Contribution entries | 5
Main challenge | Keeping the architecture, use case, sequence, ERD and interface artefacts — produced across LucidChart, Draw.io and Figma — consistent with each other and with the SRS; addressed with a Design Alignment Table. Individual contribution hours for Phase 2 were not broken down per student in this workbook. | Verified entries | 5
Next planned activity | Begin Phase 3: development, integration, testing and demonstration, building on the approved Phase 2 design; record individual contributions and hours per student as work happens. | Unverified entries | 0
|  | Stakeholder engagements | 0

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student(s) | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | LE Letsie | 25/08/2026 | 26/08/2026 | Completed | 100 | Signed Stakeholder Cooperation & Information Use Agreement (Appendix B) with Mister Auto & Turbo, dated 25/08/2026. | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | RG Madi | 25/08/2026 | 26/08/2026 | Completed | 100 | SRS Section 3 (Problem Statement), Section 9 (Current Process and Diagram) and Appendix D (Current Process Evidence). | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | NM Netshituka | 25/08/2026 | 26/08/2026 | Completed | 100 | SRS Section 4 (Aim and Objectives) and Section 5 (Project Scope). | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | LE Lipali | 25/08/2026 | 26/08/2026 | Completed | 100 | Stakeholder needs SN-01–SN-05 documented in SRS Section 8.2, drawn from prepared interview/engagement questions. | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | LTBG Pule | 25/08/2026 | 26/08/2026 | Completed | 100 | SRS Appendix C (Stakeholder Interview Findings) and Section 8.2 (Stakeholder Needs). | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | Group | 25/08/2026 | 26/08/2026 | Completed | 100 | This Web Vortex WIL document — full initial SRS including scope, functional/non-functional requirements, system requirements, integration requirements and MoSCoW prioritisation. | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | LE Letsie |  |  | Completed | 100 |  | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | LE Lipali | 30/08/2026 | 30/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | LE Lipali | 30/08/2026 | 30/08/2026 | Completed | 100 |  | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | Group | 27/08/2026 | 31/08/2026 | Completed | 100 | This progress tracker workbook, being completed from the SRS. | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | Group | 28/08/2026 | 28/08/2026 | Completed | 100 |  | Yes |  | Completed
U2-01 | Phase 2 | Activity 2.1 | Design the system architecture | Group | 01/09/2026 | 20/09/2026 | Completed | 100 | System Architecture Diagram (LucidChart) — Web Vortex Phase 2 System Design, Section 8 (Original Design Source Links). | Yes |  | Completed
U2-02 | Phase 2 | Activity 2.1 | Model the system use cases | Group | 01/09/2026 | 20/09/2026 | Completed | 100 | Use Case Diagram (Draw.io) and Use Case Summary — Web Vortex Phase 2 System Design, Section 4. | Yes |  | Completed
U2-03 | Phase 2 | Activity 2.1 | Design the sequence diagrams (Flutter↔Supabase and ASP.NET↔Supabase) | Group | 01/09/2026 | 20/09/2026 | Completed | 100 | Sequence Diagram 1 (Flutter ↔ Supabase) and Sequence Diagram 2 (ASP.NET ↔ Supabase), LucidChart — Section 8. | Yes |  | Completed
U2-04 | Phase 2 | Activity 2.2 | Design the database (Entity Relationship Diagram) | Group | 01/09/2026 | 22/09/2026 | Completed | 100 | ERD (LucidChart) and Database Entity Summary — Web Vortex Phase 2 System Design, Section 5. | Yes |  | Completed
U2-05 | Phase 2 | Activity 2.2 | Design the Flutter mobile interface | Group | 01/09/2026 | 22/09/2026 | Completed | 100 | Flutter Mobile Interface Design (Figma) — Section 8 Original Design Source Links. | Yes |  | Completed
U2-06 | Phase 2 | Activity 2.2 | Design the ASP.NET web interface | Group | 01/09/2026 | 22/09/2026 | Completed | 100 | ASP.NET Web Interface Design (Figma) — Section 8 Original Design Source Links. | Yes |  | Completed
U2-07 | Phase 2 | Activity 2.3 | Compile the Design Alignment Table and Phase 2 System Design document | Group | 20/09/2026 | 24/09/2026 | Completed | 100 | Web Vortex Phase 2 System Design document, Section 7 (Design Alignment Table) linking requirements, use cases, ERD entities and interfaces. | Yes |  | Completed
U2-08 | Phase 2 | Activity 2.3 | Obtain stakeholder review and sign-off of the Phase 2 design | Group | 25/09/2026 | 25/09/2026 | Completed | 100 | Stakeholder Review & Approval — Phase 2 System Design, signed by Motlokoa Tsotesi and all group members, 25/09/2026. | Yes |  | Completed
U2-09 | Phase 2 | Activity 2.3 | Update the GitHub repository with Phase 2 design artefacts | Group | 20/09/2026 | 25/09/2026 | Completed | 100 | https://github.com/Inheritancersa/MisterAutoAndTurbo — "Phase 2 updates." | Yes |  | Completed
U2-10 | Phase 2 | Activity 2.3 | Complete the progress report and contribution record for Phase 2 | Group | 25/09/2026 | 25/09/2026 | Completed | 100 | This progress tracker workbook, updated from the Web Vortex Phase 2 System Design document. | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
LE Letsie | 224099468 | Unit 1 / Phase 1 | Stakeholder Identification | Coordinate stakeholder engagement | Confirmed stakeholder and agreement | 26/08/2026 | 3 | Stakeholder agreement | YES | 26/08/2026
LE Lipali | 215135458 | Unit 1 / Phase 1 | Interview Prep | Prepare questions | Created interview questions | 26/08/2026 | 3 | Interview notes | YES | 26/08/2026
LTBG Pule | 219002738 | Unit 1 / Phase 1 | Stakeholder Interview | Collect requirements | Captured stakeholder needs | 26/08/2026 | 3 | Stakeholder discussion | YES | 26/08/2026
NM Netshituka | 223013773 | Unit 1 / Phase 1 | Scope Definition | Define objectives and scope | Prepared aims and objectives | 26/08/2026 | 3 | Project document | YES | 26/08/2026
RG Madi | 222066543 | Unit 1 / Phase 1 | Requirements | Document current process/problem | Compiled problem statement | 26/08/2026 | 3 | WIL document | YES | 26/08/2026

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
25/08/2026 | Unit 1 / Phase 1 | Meeting | Confirm stakeholder cooperation and sign the Stakeholder Cooperation & Information Use Agreement | LE Letsie, LE Lipali, LTBG Pule, NM Netshituka, RG Madi | Motlokoa Tsoetsi (Managing Director) | Stakeholder confirmed willingness to participate; agreed information-sharing terms and the prototype to be provided in return. | File signed agreement; proceed with requirements interviews. | Signed Stakeholder Cooperation & Information Use Agreement (SRS Appendix B).
25/08/2026 | Unit 1 / Phase 1 | Meeting | Gather requirements and understand the current manual, paper-based workshop process | LE Letsie, LE Lipali, LTBG Pule, NM Netshituka, RG Madi | Motlokoa Tsoetsi (Managing Director) | Identified stakeholder needs SN-01 to SN-05: remote progress tracking, fixed/transparent pricing, customer-supplied vs shop-supplied part cost breakdown, need for stronger digital presence, and centralised repair history. | Incorporate findings into the SRS problem statement, scope and requirements. | SRS Appendix C (Stakeholder Interview Findings), Section 8.2, Appendix D (Current Process Evidence).
25/08/2026 | Unit 1 / Phase 1 | Meeting | All group members | Motlokoa Tsoetsi - Managing Director | Discussed current process, pricing issues, repair tracking and online presence needs | Draft SRS and validate requirements | Signed agreement and notes
25/09/2026 | Phase 2 | Meeting | Review and approve the Phase 2 system design (architecture, UML, ERD and interface designs) | LE Letsie, LE Lipali, LTBG Pule, NM Netshituka, RG Madi | Motlokoa Tsotesi (Owner, Mr Auto & Turbo) | Stakeholder reviewed the System Architecture Diagram, Use Case Diagram, Sequence Diagrams, ERD, Flutter Mobile Interface Design and ASP.NET Web Interface Design; confirmed the design reflects the business needs and workflow discussed, and approved the group to proceed to the next phase of development. | File the signed Stakeholder Review & Approval — Phase 2 System Design page; proceed to Phase 3 development. | Stakeholder Review & Approval — Phase 2 System Design (signed page, Web Vortex WIL document, 25/09/2026).

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
25/08/2026 | Unit 1 / Phase 1 | Group members' current skill level in Flutter, ASP.NET and Supabase (documented constraint). | Risk of slower development once the project moves into design and build phases. | Self-study and small practice builds in each technology alongside requirements work. | LE Letsie | 26/08/2026 | Resolved
25/08/2026 | Unit 1 / Phase 1 | Stakeholder's business is entirely paper-based with no existing digital or online records. | Made it harder to gather structured requirements and cost/pricing data quickly. | Relied on direct interviews, observation of the manual process and written confirmation (WhatsApp/meeting notes) per the Cooperation Agreement. | LE Lipali | 26/08/2026 | Resolved
25/08/2026 | Unit 1 / Phase 1 | Limited time with stakeholder | Delayed requirements clarification | Schedule follow-up session and consolidate questions | LTBG Pule | 26/08/2026 | Resolved
20/09/2026 | Phase 2 | Keeping the architecture, use case, sequence, ERD and interface artefacts (built across LucidChart, Draw.io and Figma) consistent with one another. | Risk of the design documents contradicting each other and failing the rubric's consistency requirement. | Built a Design Alignment Table cross-referencing each requirement to its use case, ERD entity and interface, and reviewed it with the stakeholder before sign-off. | Group | 24/09/2026 | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Phase 2 | Initial or updated SRS completed | Yes
Reporting period | 01/09/2026 - 25/09/2026 | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | No
What was completed during this phase? | System architecture, use case, sequence and entity-relationship diagrams completed; Flutter mobile and ASP.NET web interface designs completed in Figma; a Design Alignment Table linking requirements, use cases, database entities and interfaces was compiled; and the Phase 2 System Design was reviewed and signed off by the stakeholder, Motlokoa Tsotesi, on 25/09/2026. | Stakeholder engagement recorded | Yes
What remains incomplete? | Individual contribution hours for Phase 2 have not yet been broken down per student in this workbook; the group has not yet confirmed the Microsoft Project schedule or confidential peer evaluation are up to date for this phase. | Challenges and actions updated | Yes
Why is it incomplete? | Phase 2 effort focused on completing and validating the design artefacts and obtaining stakeholder sign-off before the phase closed, so per-student hour logging was not completed in this workbook this phase. | Group reflection completed | Yes
Which contributions were particularly important? | The stakeholder's review and sign-off of the Phase 2 System Design, confirming the architecture, ERD and interface designs reflect the actual business needs before development begins. | Microsoft Project updated | To confirm
Were there participation concerns? | No major concerns identified. | GitHub evidence available | Yes
What will the group improve in the next phase? | Record individual contributions and hours per student as work happens during Phase 3, and confirm the Microsoft Project schedule and GitHub repository fully reflect the Phase 2 artefacts. | Confidential peer check completed | To confirm
Main priority for the next phase | Begin Phase 3: development, integration, testing and demonstration.

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Phase 2 | Length | Approximately 400–600 words in total.
Project title | Vehicle Service Management System (VSMS) for Mister Auto & Turbo | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | We learned how to translate the SRS requirements into a coherent architecture, UML, ERD and interface design, and to prove traceability between them using a Design Alignment Table. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | The stakeholder review went well because the design artefacts were validated against the SRS before the meeting, so the stakeholder could confirm the design matched the real workflow and approve it without major changes. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | Keeping the architecture, use case, sequence, ERD and interface artefacts — built across LucidChart, Draw.io and Figma — consistent with each other was difficult. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Tasks were divided by design artefact (architecture diagram, use case diagram, sequence diagrams, ERD, Flutter mobile interface, ASP.NET web interface) and consolidated into one Phase 2 System Design document.
Did all members contribute fairly? Explain. | Members contributed fairly; however individual hours were not logged per student in this workbook for Phase 2 and should be recorded in Phase 3.
How did the group handle disagreements or delays? | The group communicated regularly and used the stakeholder review to validate and resolve open design questions.
What did the group learn from the stakeholder? | The stakeholder confirmed the proposed roles (Administrator/Manager, Receptionist, Mechanic, Customer) and workflows matched real operations, and approved the group to proceed to development.
Improvement action 1 for the next phase | Log individual contributions and hours per student throughout Phase 3.
Improvement action 2 for the next phase | Confirm the GitHub repository and Microsoft Project schedule fully reflect the Phase 2 artefacts before Phase 3 begins.
Priority for the next phase | Move from design into development, integration and testing (Phase 3).